Complexity of WPS-SP

Proposition. The recognition version of the Work Package Sizing Problem under Strict Precedence (WPS-SP) on an acyclic task network is unary NP-complete, even when each task has equal work content and duration, xi=ti. Consequently, the corresponding cost-minimization problem is unary NP-hard.

Proof sketch. Membership in NP is immediate: given a partition of tasks into work packages, one can verify in polynomial time that every task is assigned exactly once, the induced strict-precedence work-package network is acyclic, the project meets its deadline, and the total cost does not exceed a prescribed threshold.

For NP-hardness, reduce from 3-PARTITION. Given 3l integers si satisfying

B4<si<B2,

i=13lsi=lB,

construct a WPS-SP instance with 3l active tasks and only dummy start/end tasks as inactive tasks. There are no precedence relations among the active tasks; each is connected only from the dummy source and to the dummy sink. Set

xi=ti=si,d=B,

and choose the cost parameters

ω=1,ξ=0,α=0,

with

gx=0,   0≤x≤B+∞,   x≥B, fx=gx=0

and cost threshold Z=l.

Because the active tasks have no mutual precedence relations, the deadline d=B is satisfied regardless of how feasible work packages are formed. A solution has total cost at most l only if:

1. no work package has work content greater than B; and

2. at most l work packages are used.

Since the total work content is exactly

i=13lsi=lB,

these conditions force exactly l work packages, each with total work content exactly B. Moreover, because

B4<si<B2,

each work package must contain exactly three tasks. Therefore, a WPS-SP solution with total cost at most l exists if and only if the original 3-PARTITION instance can be partitioned into l triples, each summing to B.

3-PARTITION≤pWPS-SP,

so the recognition version of WPS-SP is unary NP-complete, and the corresponding optimization problem is unary NP-hard.□