Problem Statement

Consider a production or engineering project consisting of a set of elemental tasks N, such as component preparation, fabrication, assembly, integration, inspection, and other project activities. Each task i∈N has a known duration ti, workload xi, and technological precedence relationships with other tasks. Before the project is executed, the manager must group these tasks into work packages W1,…,Wp, each of which is managed and scheduled as a single organizational unit. The paper defines work content as the sum of the constituent task workloads and treats the work-package duration according to the critical path of its internal tasks.

Under strict precedence, if a task in work package Wi must precede a task in Wj, then Wj cannot proceed until Wi is completed. Consequently, combining tasks into larger packages can reduce opportunities for parallel production and increase the overall project duration. The decision is therefore to determine the number p and composition of the work packages so as to balance management overhead, estimation and monitoring costs, economies of scale, cash-flow effects, and loss of scheduling flexibility, while ensuring that the resulting work-package sequence is feasible and that the project is completed by deadline d. The objective is to minimize total project cost TC.