Problem Description

A production project consists of a set of activities N=1,…,n, such as fabrication, assembly, inspection, and testing. Each activity i∈N has a fixed processing time pi and requires rik units of renewable resource k∈K, whose available capacity is Rk. Technological dependencies between activities are represented by a precedence set E, where i,j∈E indicates that activity j cannot start until activity i is completed. Activities may be processed in parallel when precedence requirements are satisfied, provided that the total resource usage at any time does not exceed the corresponding capacity Rk. Once started, an activity cannot be interrupted. The scheduling decision is to determine the start time Si of each activity i. The Resource-Constrained Project Scheduling Problem (RCPSP) seeks a feasible schedule satisfying all precedence and resource-capacity constraints while minimizing the project makespan Cmax, i.e., minCmax.